## Sheet1
Task # | Task Description | Duration | Uncertainty Min | Uncertainty Max | Cost | Uncertainty
1 | Requirements Development | 3 weeks | 0.5 weeks | 1.5 weeks | $50k | $5k-$10k
2 | RFP Preparation | 5 weeks | 1 week | 2 weeks | $60K | $7k - $12k
3 | Proposals from vendors | 8 weeks | 0.5 weeks | 1 week | 0 | $0-0
4 | Proposal Evaluation | 4 weeks | 1 week | 2 weeks | $50k | $5k - $10k
5 | Contract negotiation | 5 weeks | 2 weeks | 3 weeks | $30k | $2k - $5k
6 | Preliminary Design | 40 weeks | 5 weeks | 10 weeks | $5000k | $700k - $1500k
7 | Crtical Design | 30 weeks | 5 weeks | 7 weeks | $4000k | $500k - $1000k
8 | Flight Development | 45 weeks | 10 weeks | 15 weeks | $4500k | $1000k - $2000k
9 | Integration & Test | 20 weeks | 10 weeks | 20 weeks | $2500k | $1000k-$2000k